## Sheet1 (hidden)
Serial | BL | PO | Supplier | Lot SKD # (stelantis) | Order # | Lot# | Shipping by | Shipping line/Air line | Doc | CI | Form 4 | Nafeza / Cargo X | ACID number | Sent request to Finace | Shipment items | POL | POD | tracing date | Pick up | ETS | ETA | Mobica Plant | AAV Plant | current status | Delivered on
1 | 065-44520722 | Not yet | Adient Zaragoza, Spain:21004595 |  | X0 |  | Airfreight | Saudi Arabian Airlines | With shipemnt | 4868 | 2024-12-19 | No need | No need | Done | L2 & L3 opt. Carsets | Madrid | Cairo Airport | 2024-12-23 |  | 2024-10-17 | 2024-10-29 |  |  | Delivered | 2025-01-23
1 | 065-44529133 | 4500129739 | Tesca Spain Barcelona, Spain: 21004605 |  | X2+X0 |  | Airfreight | Saudi Arabian Airlines | Recived | 2986.36 | Done | No need | No need | 2024-12-23 | Fabrics | Barcelona | Cairo Airport | 2024-12-23 |  | 2024-12-12 | 2024-12-22 | 2025-02-04 |  | Delivered
1 | 147 2047 5630 | 4500129825 | Sage Kenitra, Morocco:21004625 |  | X2+PV |  | Airfreight | ROYAL AIR MAROC | 2025-01-19 | 6735 | Not yet | No need | No need | 2024-12-24 | Fabrics | Casablanca Mohamed V | Cairo Airport | 2024-12-23 |  | 2024-12-21 | 2024-12-23 | 2025-02-04 |  | Delivered
1 | 065-44531141 | 4500129799 | Adient Zaragoza, Spain:21004595 |  | X2A(10 L3 Opts. Carsets) |  | Airfreight | Saudi Arabian Airlines | Recived | 7585.75 | Not yet | No need | No need | 2024-12-24 | L3 opt. Carsets | Madrid | Cairo Airport | 2024-12-23 |  | 2024-12-20 | 2024-12-25 |  |  | Delivered | 2025-01-22
1 | 176-96608315 | 4500129827 | Apollo (Sage italy plant):21004626 |  | X2+PV |  | Airfreight | EMIRATES | Recived | 3346 | Done | No need | No need | 2024-12-24 | Fabrics | MALPENSA, Milano | Cairo Airport | 2024-12-23 |  | 2024-12-20 | 2024-12-30 | 2025-02-04 |  | Delivered
1 | 147-20476816 | 4500130076 | Adient Keintra, Morocco: 21004640 |  | Milestones |  | Airfreight | ROYAL AIR MAROC | 2025-01-19 | 19860.46 | Not yet | No need | No need | 2025-01-06 | Fabrics | Casablanca Mohamed V | Cairo Airport | 2025-01-06 |  | 2025-01-07 | 2025-01-12 | 2025-02-04 |  | Delivered
1 | 065-38610176 | 4500130093 | Adient Zaragoza, Spain:21004595 |  | PV ( without airbags) |  | Airfreight | Saudi Arabian Airlines | Recived | 18034.77 | Done | No need | No need | 2025-01-22 | Carsets | Barcelona | Cairo Airport | 2025-02-02 |  | 2025-01-22 | 2025-01-25 | 2025-02-05 |  | Delivered
1 | 057-13614904 | 4500130093 | Adient Zaragoza, Spain:21004595 |  | PVs' Airbags |  | Airfreight | Air France | With shipemnt | 11930 | Not yet | No need | No need | 2025-01-22 | Airbags | Barcelona | Cairo Airport | 2025-02-02 |  | 2025-01-30 | 2025-02-04 | 2025-02-11 |  | Delivered
1 | 065-44534814 | 4500130221 | Adient Zaragoza, Spain:21004595 |  | X2B (Without airbags) |  | Airfreight | Saudi Arabian Airlines | With shipemnt | 36364.61 | Not yet | No need | No need | 2025-02-02 | 5 L2 Carstes | Barcelona | Cairo Airport | 2025-02-02 |  | 2025-01-31 | 2025-02-07 | 2025-02-17 |  | Delivered
1 |  | 4500130304 | Adient Zaragoza, Spain:21004595 |  | X3&BM |  | Airfreight |  |  |  | Not yet | No need | No need |  | 23 L2 & 22 L3 Opts Carstes | [8 empty] | Delivered
1 | SGCU 512128.2 | 4500130464 | Apollo (Sage italy plant):21004626 |  | March & April SOP | 1 to 10 | Seafright | mediterranean | Recived | 32210.3 | Done | Done | 2050804802025020169 | Done | Fabrics |  |  | 2025-03-25 | Done | 2025-02-26 | 2025-03-12 | 2025-03-26 | 2025-03-26 | Delivered | 2025-03-26
1 | 299-17362026 | 4500130768 | Tesca Spain Barcelona, Spain: 21004605 |  | March & April SOP | 1, 2 | Airfreight | Kuwait air lines | Recived | 7298.15 | Not yet | No need | No need | Done | Fabrics |  |  | 2025-03-25 | Done | 2025-03-21 | 2025-03-23 | 2025-04-09 |  | Delivered | 2025-04-10
1 | 299-17379331 | 4500130781/ new(4500131437)new | Adient Keintra, Morocco: 21004640 |  | March & April SOP | 1, 2 | Airfreight | Kuwait air lines | Recived | 20070.72 | Not yet | No need | No need | Done | Fabrics & Fabrics Acc |  |  | 2025-03-25 | Done | 2025-03-17 | 2025-03-22 | 2025-04-09 |  | Delivered | 2025-04-11
1 | 077-56655616 | 4500130822 | Sage Kenitra, Morocco:21004625 |  | March & April SOP | 1, 2 | Airfreight | Egypt air line | Recived | 9900 | Not yet | No need | No need | Done | Fabrics |  |  | 2025-03-25 | Done | 2025-03-21 | 2025-03-26 | 2025-04-09 |  | Delivered | 2025-04-10
1 | CMAU3922735-TCNU2840130 | 4500130593 | Adient Zaragoza, Spain:21004595 |  | March & April SOP | 1 to 10 | Seafright | CMA | Recived | 93266.91 | Done | Done | 2050804802025020235 | Done | Carstes | Barcelona | Alexandria | 2025-03-25 | Done | 2025-03-04 | 2025-03-26 | 2025-04-08 |  | Delivered | 2025-04-10
7 |  | Created | Adient Keintra, Morocco: 21004640 |  | April to May | 1 to 10 | Airfreight |  | Not yet |  | Not yet | No need | No need | Bank confirmed | Trim covers and Threads |  |  |  | Done | 2025-04-18 | 2025-04-19 | 2025-05-06 |  | Delivered | 2025-05-07
8 |  | Created | ASAI |  | Tester machine |  | Airfreight |  | Recived | 66045.82 | Not yet | No need | No need | Bank confirmed | Tester Machine |  |  |  | Done | 2025-04-15 | 2025-04-19 | 2025-05-06 |  | Delivered | 2025-05-06
1 | CMAU6589546 TGBU5084972 BEAU6306000 | 4500130996 | Adient Zaragoza, Spain:21004595 |  | May & April SOP | 1 to 10 | Seafright | CMA | Sent | 89490.75 | in process | Done | 2050804802025030101 | Bank confirmed | Carstes (3x40) |  |  |  | Done | 2025-04-18 | 2025-05-02 | 2025-05-13 |  | Delivered | 2025-03-15
10 |  | 4500131471 | Sage Kenitra, Morocco:21004625 |  | March to November SOP |  | Airfreight | Casblanca airport | Not yet |  | in process | Not yet | No need | Bank confirmed | Fabrics |  | 2025-04-28 |  | Done | 2025-05-07 | 2025-05-08 | 2025-05-19 |  | Delivered | 2025-05-25
11 |  | 4500131583 | Sage Kenitra, Morocco:21004625 | March to November SOP | March to November SOP |  | Airfreight | Casblanca airport | Sent |  | Not yet | No need | No need | Bank confirmed | Fabrics | 2025-05-15 | 2025-05-17 | 2025-05-22 | Done | 2025-05-15 | 2025-05-17 | 2025-05-22 |  | Delivered | 2025-05-25
2 | TLLU4543379 CRSU9204090 TCNU5807541 ECMU4793506 CMAU9761577 | 4500131009 | Adient Zaragoza, Spain:21004595 |  | May & June | 5 to 15 | Seafright | CMA | Not yet | 240817.3 | in process | Done | 2050804802025040183 | Bank confirmed | Carstes (5x40) |  |  |  | Done | 2025-04-23 | 2025-05-11 | 2025-05-21 |  | Delivered | 2025-05-23
4 | MRKU 282682/3 MRSU 435908/4 TGHU 984865/9 MRSU 504459/0 | 4500131337 | Adient Keintra, Morocco: 21004640 |  | March to November SOP | Year 2025 | Seafright | Maersk | Recived |  | Done | Done | 2050804802025040217 | Bank confirmed | Fabrics Acc (4x40) |  | Done |  | Done | 2025-04-27 | 2025-05-15 | 2025-05-27 |  | Delivered | 2025-05-30
8 | ARKU8463419 | 4500131330 | Sage Kenitra, Morocco:21004625 |  | March to November SOP | 1 to 15 | Seafright | Arkas | Sent |  | in process | Done | 2050804802025040258 | Bank confirmed | Fabrics(1x40) |  |  |  | Done | 2025-05-09 | 2025-05-25 | 2025-05-30 |  | Delivered | 2025-06-01
| - | Created | Adient Zaragoza, Spain:21004595 |  | May & April SOP | 1 to 10 | Airfreight |  | Sent |  | in process | No need | No need | Bank confirmed | Carstes ( Airbags) |  |  |  | Done |  | 2025-05-10 | 2025-05-26 |  | Delivered
|  | 4500131562 | Adient Zaragoza, Spain:21004595 |  | March to November SOP | 15 to 25 | Seafright | CMA | ✓ | 189898.3409 | in progress | ✓ | 2050804802025050141 | NBE | Carstes (5x40) |  | 2025-05-16 |  | ✓ | 2025-05-19 | 2025-06-11 | 2025-06-21 |  | In transit
|  | 4500131652 | Adient Zaragoza, Spain:21004595 |  | March to November SOP | - | Seafright | CMA |  | 303696.1996 |  | ✓ | 2050804802025050307 | NBE | Carstes (5x40) |  |  |  | ✓ | 2025-05-30 | 2025-06-16 |  |  | In transit
|  | 4500131746 | Adient Zaragoza, Spain:21004595 |  | March to November SOP | - | Seafright | CMA |  | 248450.8174 |  |  | 2050804802025050398 | ? | 4*40 |  |  |  | ✓ | 2025-05-30 | 2025-06-16 |  |  | In transit
|  |  | Adient Zaragoza, Spain:21004595 |  | March to November SOP | - | Seafright |  |  | 47806.42 |  |  | 2050804802025060017 |  | 1*40 |  |  |  | 2025-06-04 |  |  |  |  | Waiting for pick up
|  |  | Adient Zaragoza, Spain:21004595 |  |  |  | Seafright |  |  | 48400 |  |  |  |  | 1*20 |  |  |  | 2025-06-04 |  |  |  |  | Waiting for pick up
5 | MSKU 919113/5 MRKU 779936/1 | 4500131609 | Adient Keintra, Morocco: 21004640 |  | March to November SOP | 5 to 25 | Seafright | Maersk | Sent |  | in process | Under revsion | 2050804802025050026 | Bank confirmed | Fabrics Acc and trim covers (1x40) & (1x20) |  | Done |  | Done | 2025-05-11 | 2025-05-25 | 2025-06-04 |  | CC
|  | Not yet | Adient Keintra, Morocco: 21004640 |  | March to November SOP |  | Seafright | Maersk | Not yet |  | Not yet | Not yet | 2050804802025050448 | Not yet | Fabrics Acc (1x40) |  |  |  | 2025-06-02 |  |  |  |  | Waiting for pick up
6 | LCL | 4500131113 | Tesca Spain Barcelona, Spain: 21004605 |  | March to November SOP |  | Seafright | Co-loader | ✓ | 24692.28 | ✓ | ✓ | 2050804802025030317 | Suez Canal Bank | Fabrics(LCL) |  |  |  | Done | 2025-04-27 | 2025-05-30 | 2025-06-04 |  | CC
7 |  | Not yet | Tesca Moroco |  | March to November SOP |  | Seafright |  | Not yet |  | Not yet | Not yet | 2050804802025050067 |  | Fabrics(LCL) |  |  |  | Done | 2025-05-30 | 2025-06-19 | 2025-06-24 |  | In transit
9 | SUDU6650358 | 4500131609 | Sage Kenitra, Morocco:21004625 |  | March to November SOP |  | Seafright | Maersk | Sent |  | Done | Done | 2050804802025050018 | Bank confirmed | Fabrics(1x40) |  | 2025-04-28 |  | Done | 2025-05-25 | 2025-06-07 | 2025-06-12 |  | In transit
9 | MRSU4738468 | 4500131792 | Sage Kenitra, Morocco:21004625 | March to November SOP | March to November SOP |  | Seafright | Maersk | Not yet |  | Not yet |  | 2050804802025050323 | Not yet | Fabrics(1x40) | 2025-05-24 | 2025-06-11 | 2025-06-16 | Done | 2025-05-25 | 2025-06-07 | 2025-06-12 |  | In transit
9 |  | Not yet | Sage Kenitra, Morocco:21004625 | March to November SOP | March to November SOP |  | Seafright | Maersk | Not yet |  | Not yet |  | 2050804802025050406 | Not yet | Fabrics(1x40) |  |  |  | Done | 2025-06-03 | 2025-06-15 | 2025-06-20 |  | In transit
|  | Not yet | Sage Kenitra, Morocco:21004625 |  | March to November SOP |  | Seafright | Maersk | Not yet |  | Not yet |  | 2050804802025050414 | Not yet | Fabrics(1x40) |  |  |  | Done |  |  |  |  | In transit
12 |  |  | Apollo (Sage italy plant):21004626 |  | March to November SOP |  | Seafright | CMA | ✓ | 45629.89 |  |  |  | ? | Fabrics |  | 2025-04-28 |  | Done | 2025-05-27 | 2025-06-11 | - |  | In transit
Upcoming Shipemnts (ISA)
1 |  |  | Adient Keintra, Morocco: 21004640 |  | August to sep | [13 empty] | June 23rd to 29th |  |  |  |  | Waiting for items to be ready for pick up
1 |  |  | Adient Keintra, Morocco: 21004640 |  | Sep to OCT | [13 empty] | July 28th to August 3rd |  |  |  |  | Waiting for items to be ready for pick up
1 |  |  | Adient Keintra, Morocco: 21004640 |  | OCT TO November | [13 empty] | August 25th to 31st |  |  |  |  | Waiting for items to be ready for pick up
1 |  |  | Adient Keintra, Morocco: 21004640 |  | November to Decmber | [13 empty] | September 29th to OCT 5th |  |  |  |  | Waiting for items to be ready for pick up
1 |  |  | Adient Keintra, Morocco: 21004640 |  | December to Jan | [13 empty] | OCT 27th to Nov 2nd |  |  |  |  | Waiting for items to be ready for pick up
1 |  | Not yet | Tesca Spain Barcelona, Spain: 21004605 |  | March to November SOP |  | Seafright | [9 empty] | Done |  | (Week 24) June 9 to June 15 |  |  |  |  | Waiting for items to be ready for pick up
1 |  | Not yet | Tesca Spain Barcelona, Spain: 21004605 |  | March to November SOP |  | Seafright | [9 empty] | Done |  | (Week 26) June 23 to June 25 |  |  |  |  | Waiting for items to be ready for pick up
1 |  | Not yet | Tesca Moroco |  | March to November SOP |  | Seafright | [9 empty] | 2025-06-29 |  | 2025-06-04 |  |  |  |  | All three shipemnts will be picked in one shipment
1 |  | Not yet | Tesca Moroco |  | March to November SOP |  | Seafright | [9 empty] | 2025-06-29 |  | 2025-06-04 |  |  |  |  | All three shipemnts will be picked in one shipment
1 |  | Not yet | Tesca Moroco |  | March to November SOP |  | Seafright | [9 empty] | 2025-06-29 |  | 2025-06-04 |  |  |  |  | All three shipemnts will be picked in one shipment
Formulas:
ETA = [ETS]+5
Mobica Plant = [ETA]+5
Note on S12: dell: 16-3-2025/ETA:12-3-2025/ Mobica plant : 22-3-2025
Note on S16: dell: 16-3-2025/ُETA:17-3-2025

## Automotive Accounts
Account
GM
BMW & Geely
MEC & Exeed
Nissan
Cherokee & Toyota
Citroen
Proton
Kassrawy
Train & Bus
GHB&I vend
Dong Feng

## Citroen's Suppliers
SN | Supplier | country | Estimated Time (day)
|  |  | Manufacturing time | transit time | customs clearance | receiving inspection
1 | Sage Kenitra, Morocco:21004625 | Morocco | 25 | 20 | 10 | 5
2 | Adient Keintra, Morocco: 21004640 | Morocco | 35 | 20 | 10 | 5
3 | Adient Zaragoza, Spain: 21004595 | Spain | 45 | 12 | 10 | 5
4 | Apollo (Sage italy plant):21004626 | Italy | 25 | 10 | 10 | 5
5 | Tesca Morocco:21004835 | Morocco | 30 | 15 | 10 | 5
6 | Tesca Spain Barcelona, Spain: 21004605 | Spain | 30 | 12 | 10 | 5